## UAT_FEEDBACK_TRACKER
HKIT COURSE EXEMPTION ANALYZER
User Feedback & UAT Tracker |  |  | Tester |  |  | Developer | Developer
Date | Particular | Feature/Function | Category | Comments | Priority | Status | Developer Comments
2025-11-03 | Upload Small PDF - Testing | File Upload & Processing | UAT Testing |  |  | Tested | around 37s
2025-11-03 | Upload Large Image PDF (>4.5MB) - Testing | File Upload & Processing | UAT Testing |  |  | Tested | around 40.7s
2025-11-03 | PDF File - Testing | File Upload & Processing | UAT Testing |  |  | Tested
2025-11-03 | View Transcripts - First Click | View Transcripts | UAT Testing |  |  | Tested | still needs to reopen couple times to start redenering after started the analysis
2025-11-03 | View Transcripts - All Pages Display | View Transcripts | UAT Testing |  |  | Tested
2025-11-03 | Select Programme & Fill Student Info | Programme Selection | UAT Testing |  |  | Tested
2025-11-03 | AI Analysis - Small Transcript | AI Analysis | UAT Testing |  |  | Tested
2025-11-03 | AI Analysis - Large Image PDF | AI Analysis | UAT Testing |  |  | Tested
2025-11-03 | Check Exemption Results Display | Results Display | UAT Testing |  |  | Tested
2025-11-03 | Language Exemptions & 50% Rule | Results Display | UAT Testing |  |  | Tested
2025-11-03 | Edit Results Mode | Edit Mode | UAT Testing |  |  | Tested
2025-11-03 | Generate Study Plan | Study Plan | UAT Testing |  |  | Tested | Still need to confirm with the logic for each programme
2025-11-03 | Export to CSV | Export Functions | UAT Testing |  |  | Tested
2025-11-03 | Export to Excel Application | Export Functions | UAT Testing |  |  | Tested
2025-11-03 | Export to PDF Application | Export Functions | UAT Testing |  |  | Tested
2025-11-03 | Clear All & Restart | Reset Functionality | UAT Testing |  |  | Tested
2025-11-03 | Technical Support Link | Footer/Support | UAT Testing |  |  | Tested